## Risk- Requirement
Erste - APIM Consulting (C100012800003022)
Sl. No. | Type | Description | Status | Owner | Target Date | Comments
1 | Resource allocation | Backend developer for developer portal
2 | Resource allocation | UI/UX developer for developer portal

## Operations
Leave :
Resource Name | Role | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Pooja Joshi | Role: PCEO
Sourav Majumdar | Role: Scrum Master/developer; Jan: 14
Ankita Choudhury | Role: Lead/developer
Mohit Joshi | Role: Testing
Sachin M | Role: Architect
Ahini Roy | Role: Developer; Feb: 7,8,9
Parul Sharma | Role: Java Developer; Jan: 10 to 14
Timesheet:
| Role | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Public Holidays(Date) | 26 | NA | 18 | NA | NA | NA | NA | 11,15 | NA | 5,24,25 | NA | NA
| Working days(no of days) | 20 | 20 | 22 | 21 | 22 | 22 | 21 | 21 | 22 | 18 | 22 | 22
Resource Name | Role | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Pooja Joshi | Role: PCEO
Sourav Majumdar | Role: Scrum Master/developer
Ankita Choudhury | Role: Lead/developer
Mohit Joshi | Role: Testing
Sachin M | Role: Architect
Ahini Roy | Role: Developer
Parul Sharma | Role: Java Developer

## Project Plan -2022
Epics | High Level description of Work | Detailed description | Completion (Quarter) | Status | Comments
API import and Registration | Enabling the 3Scale APILM Platform with all facilities to onboard an API which involves the entire journey of APIfication Automatic deployment in 3 Scale API platform CI/CD | 1.API Import and Registration | Q1 and Q2 | In Progress
Alfa integration | Alfa IDP integration of 3 scale Developer Portal | 4. ALFA integration | Q1 and Q2 | Not Started
Operations/Monitoring | API monitoring using dynatrace,High load toxic consumer isolation and API behaviour side effects | 6 Operations/Monitoring | Q1 and Q2 | Not Started
Consumer | Consumer registration approval and deregistration | 2.Consumer onboarding | Q1 and Q2 | In Progress
Developer Portal | Facilitate Developer Portal and API Monetization with future scope for market place | 7 Developer portal | Q1 and Q2 | In Progress
Testing | Functional regression testing of services,Non Functional regression testing of services(performance, response time, etc..) and Penetration testing | 3.Testing framework | Q1 and Q2 | In Progress
Architecture, strategy and Roadmap | Definition of transistion architectures | 5 Architecture | Q1 and Q2 | In Progress
ECP | 3Scale API Plaform integration with ECP (Erste Container Platform) and OSB (Oracle service Bus) Middleware platform to establish seemless connection with legacy systems such as mainframes, database and other modern backend provider system | 8.ECP and OSB Services | Q1 and Q2 | Not Started
ECP | Micro Gateway and Side Car enablement for 3scale API gateway integration with Redhat Istio – Service Mesh east-west orchestration. |  | Q3 and Q4 | Not Started

## Project Plan - details
Epics | Deadline | WorkPackage |  | Status | Effort estimated in WP | Owner | Start Date | End Date | Comments | Effort spent | Estimated effort to completion
1.API Import and Registration | End of March | 1.1 | API discovery service Is in place for Rest and SOAP | Blocked | 15 | Parul |  |  | kafka integration and pure mainframe services is in out of scope
|  |  | 1.1.1 Setup portal SSO | Blocked |  | Alex / Parul |  |  | Integration with Alfa IDP and MB+
|  |  | 1.1.2 Setup API Search functionality | Blocked |  | Parul |  |  | Developer portal upgrade needed
|  |  | 1.1.3 Setup API Test functionality | Blocked |  | Parul |  |  | Consumer can test the API from the portal
|  | 1.3 | A provider is able to define specific Consumer API policies | Completed | 5 | Ankita/Ahini
|  |  | 1.3.1 Identify OOTB policies and how to apply them | Completed |  | Ankita/Ahini |  |  | Test all policies | 5 | -5
|  | 1.4 | Suport automatically deployment of ServiceWorkz mainframe services on S3 | Completed | 15 | Parul
|  |  | 1.4.1 Create Design workflow | Completed |  | Alex / Parul |  |  | Agree on the harvesting workflow | 3 | 0
|  |  | 1.4.2 Install and Test Kafka plugin on SWZ Jenkins | Completed |  | SWZ Team |  |  | Done by SWZ team | 1 | 0
|  |  | 1.4.3 Setup stash repo and create application | Completed |  | Parul |  |  |  | 0.5 | 0
|  |  | 1.4.4 Implement a consumer that can read from a topic | Completed |  | Parul |  |  |  | 0.5 | 0
|  |  | 1.4.5 Setup the CLJ appender | Completed |  | Parul |  |  |  | 1 | 0
|  |  | 1.4.6 Setup S3 buckets and Implement the code to write to S3 | Completed |  | Parul
|  |  | 1.4.7 Configure secret keys for s3 access | Completed |  | Parul
|  |  | 1.4.6 End to End S3 Writer Flow | Completed |  | Parul |  |  | Done and tested | 2 | 0
|  | 1.5 | Manual registration of API | Blocked | 0 |  |  |  | Waiting for Red Hat consultant
|  |  | 1.5.1 Design a workflow | Blocked
|  |  | 1.5.2 Implementation | Blocked
|  |  | 1.5.3 Documentation in Confluence | Blocked
|  | 1.6 | Support deployment of ECP Rest services on 3scale API gateway |  | 15 | Parul
|  |  | 1.6.1 Create Design workflow | In progress |  | Parul |  |  |  | 2 | 0
|  |  | 1.6.2 Create custom resources in OpenShift |  |  | ECP / Parul |  |  | Need assistance from ECP | 2 | 0
|  |  | 1.6.3 Implement an Operator in OpenShift that watches the resources |  |  | ECP / Parul |  |  | Need assistance from ECP | 5 | 0
|  |  | 1.6.4 Send notification to a kafka topic |  |  | Parul |  |  |  | 0.5 | 0
|  |  | 1.6.5 Read redcode label from namespace |  |  | Parul |  |  |  | 0.5 | 0
|  |  | 1.6.6 Configure the service account via origin template |  |  | Parul
|  |  | 1.6.7 Integrate Alfa container and call the RedDB |  |  | Parul
|  | 1.7 | Prepare deployment documentation | Backlog | 5 | Parul
|  |  | 1.7.1 SWZ API registration | Backlog |  | Parul |  |  |  | 3 | -1
|  |  | 1.7.2 ECP APISs registration | Backlog |  | Parul
|  | 1.8 | Publishing of services on 3scale API Gateway | Backlog | 40 | Parul
|  |  | 1.8.1 Setup projects in stash | Backlog |  | Parul
|  |  | 1.8.1.1 Create project in APILM | Backlog |  | Parul
|  |  | 1.8.8.1.2 Create origin and application project structure in cs-apimanagement | Backlog |  | Parul
|  |  | 1.8.2 Consume messages from kafka topic and read the specification from S3 | Backlog |  | Parul
|  |  | 1.8.2.1 Configure consumer for ar313_apilm-3scale_topic | Backlog |  | Parul
|  |  | 1.8.2.2 Retrieve the openapi specification from S3 | Backlog |  | Parul
|  |  | 1.8.3 Setup service account in openshift client access to 3scale CRD | Backlog |  | Parul
|  |  | 1.8.4 Implement client for installing APIs in 3scale | Backlog |  | Parul
|  |  | 1.8.4.1 Parse the openapi specification and create the backend/product objects | Backlog |  | Parul
|  |  | 1.8.4.2 Use the OpenShift API to create/update the resources | Backlog |  | Parul
|  |  | 1.8.5 Audit with CLJ | Backlog |  | Parul
|  |  | 1.8.5.1 Configure the logAppender | Backlog |  | Parul
|  |  | 1.8.5.2 Log errors and info to ar313_apilm-appender_topic | Backlog |  | Parul
|  | 1.9 | Traffic Throttling | Backlog | 5 | Ankita
|  |  | 1.9.1 Define usage metering and execution of throttling rules | Backlog |  | Ankita
|  | 1.10 | Charging API usage | Backlog | 2 | Sourav
|  |  | 1.10.1 Define pricing plans for APIs or packages in API Portal | Backlog |  | Sourav |  |  |  | 0 | 0
|  | 1.11 | API Scopes | Backlog | 2 | Ahini
|  |  | 1.11.1 Define how we can expose only a subset of API implementation interface. | Backlog |  | Ahini
|  |  | 1.11.2 Block access to SOAP operations or REST resources which are not in the scope. | Backlog |  | Ahini
|  |  | 1.11.3 Define different policies for multiple scopes of single API. | Backlog |  | Ahini
2.Consumer onboarding | End of April | 2.1 | Advanced searching API functionality | Blocked | 20 | Sourav |  |  | Only if augmentation of the DB data is possible. Need upgarde of the search functionality
|  |  | 2.1.1 Full text search functionality | Blocked |  | Sourav |  |  | By red code, by pad, by programm name
|  | 2.2 | Grant registration as Provider | Blocked | 30 | Ankita |  |  | We need support from RedHat
|  |  | 2.2.5 Integration of 3scale with MB+ | Blocked |  | Ankita
|  |  | 2.2.1 Design grant/deny process | Blocked |  | Ankita |  |  | Based on RBAC?
|  |  | 2.2.2 Implement backend functionality | Blocked |  | Ankita |  |  | We must persist API access rights?
|  |  | 2.2.3 Define and Agree on SLA | Blocked |  | Ankita
|  |  | 2.2.4 Auditing with CLJ | Blocked |  | Ankita
|  | 2.3 | Developer registration | Backlog | 30 | Ahini |  |  | Be able to place a request for becoming a new consumer for an API
|  |  | 2.3.1 Design API consumer relation to RED | Backlog |  | Ahini
|  |  | 2.3.2 Design and implement solution manager request/Deny flow | Backlog |  | Ahini
|  |  | 2.3.4 Auditing with CLJ | Backlog |  | Ahini
|  |  | 2.3.5 MB+ synchronization | Backlog |  | Ahini
|  | 2.4 | Lifecycle events notifications | Completed | 8 | Sourav |  |  |  | 4 | 0
|  |  | 2.4.1 Notifciations customizations | Completed |  | Sourav
|  |  | 2.4.2 JIRA customization | Completed |  | Sourav
|  |  | 2.4.3 API versioning and retiral | Completed |  | Sourav
|  |  | 2.4.4 Teams and Outlook notifications | Completed |  | Sourav
|  | 2.6 | Retrieval of Pricing Plans | Backlog | 5 | Sourav |  |  |  | 0 | 5
|  |  | 2.6.1 Design workflow for querying application plans | Backlog |  | Sourav
|  |  | 2.6.2 Implement workflow via Portal | Backlog |  | Sourav
|  | 2.7 | API try-out | Backlog | 20 | Ahini
|  |  | 2.7.1 Define requirement | Backlog |  | Ahini
|  |  | 2.7.2 Create mocks for all services | Backlog |  | Ahini
|  |  | 2.7.3 Test services | Backlog |  | Ahini
|  | 2.8 | 3Scale Datamodel Mapping | Backlog | 0 | Architect
|  |  | 2.8.1 Integration of 3scale with MB+ | Backlog |  | Architect
|  |  | 2.8.2 Design API consumer relation to RED | Backlog |  | Architect
3.Testing framework | End of April | 3.2 | Functional regression testing of services | Backlog | 20 | Mohit
|  |  | 3.3.1 Create requirements for Functional testing. | Backlog |  | Mohit |  |  | tosca team
|  |  | 3.3.2 Implement tests with ED and Nagarro team | Backlog |  | Mohit
|  | 3.3 | Non Functional regression testing of services(performance, response time, etc..) | Backlog | 20 | Mohit |  |  | seqis
|  |  | 3.3.1 Create requirements | Backlog |  | Mohit
|  |  | 3.3.2 Implement testing with ED team | Backlog |  | Mohit
|  | 3.4 | Penetration testing | Backlog | 15 | Mohit |  |  | Ask Georg and Charly. External company
|  |  | 3.4.1 Requirements for PEN testing? | Backlog |  | Mohit |  |  | Different things, not to be combined with 3scale
4 ALFA integration |  | 4.1 | Alfa IDP integration for 3scale portal | Backlog | 10 | Sachin
|  |  | 4.1.1 Configuration setup | Backlog |  | Sachin
|  |  | 4.1.2 List services that the Developer has access to based on the ROLE | Backlog |  | Sachin
|  | 4.2 | Alfa Service to Service authentication | Backlog | 0 | Architect |  |  | needs arhitecture decision, takes more than 6 months?
|  |  | 4.2.2 Implementation from Alfa Team | Backlog |  | Architect
|  |  | 4.2.3 Implementation in the API gateway. Replace access_key authentication with Alfa JWT | Backlog |  | Architect
5 Architecture | End of February | 5.1 | Definition of transistion architectures | Backlog | 30 | Sachin
|  |  | 5.1.1 Collecting architectural proposals from Red Hat | Backlog |  | Sachin
|  |  | 5.1.2 Definition of architectural model in Sparx EA | Backlog |  | Sachin |  |  | Formulate what is requred to fulfill the package
|  |  | 5.1.3 Evaluation of Tosca and Green Leaf Test Tool | Backlog |  | Sachin
|  |  | 5.1.4 patterns/guidelines for projects/consumers | Backlog |  | Sachin
|  |  | 5.1.5 Architecture migration roadmap | Backlog |  | Sachin
|  | 5.2 | Third party Gateway | Backlog |  | Sachin
|  |  | 5.1 Define requirement | Backlog |  | Sachin
|  | 5.3 | Third party APIs integration | Backlog |  | Sachin
|  |  | 5.3.1 Integration of cloud native app | Backlog |  | Sachin
|  |  | 5.3.2 Integration with custom adaptors and connectors | Backlog |  | Sachin
6 Operations/Monitoring | End of April | 6.1 | Dynatrace monitoring | Backlog | 20 | Sachin
|  |  | 6.1.1 Dynatrace setup for 3scale | Backlog |  | Sachin
|  |  | 6.1.2 Cemos integration with 3scale | Backlog |  | Sachin
|  | 6.2 | High load toxic consumer isolation | Backlog | 20 | Ankita
|  |  | 6.2.1 Define requirements for what a toxic consumer is | Backlog |  | Ankita
|  |  | 6.2.2 Monitor APICast for specific consumer high load services | Backlog |  | Ankita
|  |  | 6.2.3 Design and implement a way to isolate a toxic cosnumer | Backlog |  | Ankita
|  | 6.3 | API behaviour side effects | Backlog | 10 | Sourav
|  |  | 6.3.1 Determine API special behaviour side effects | Backlog |  | Sourav
|  |  | 6.3.2 Determine ways to avoid side effects in case any APIs are not healthy | Backlog |  | Sourav
|  | 6.4 | Scalabitlity and failover | Backlog | 2 | Sourav
|  |  | 6.4.1 Define requirement | Backlog |  | Sourav
|  | 6.5 | Rules and Procedures for API Management | Backlog | 10 | Sourav
|  |  | 6.5.1 API documentation is sufficient and understandable | Backlog |  | Sourav
|  |  | 6.5.2 Naming conventions are defined and agreed upon | Backlog |  | Sourav
|  |  | 6.5.3 Automated detection of breaking changes in API | Backlog |  | Sourav
|  |  | 6.5.4 Automated detection of duplicates | Backlog |  | Sourav
7 Developer portal | End of April | 7.1 | Explore different Design Tools that can be used to design the web pages of Developer Portal. | Backlog | 15
|  |  | 7.1.1 Identify and select the rite design tools for UX/UI components building such as Wireframes, Templates etc | Backlog
|  |  | 7.1.2 Check the identified design tools compatibility with Redhat 3Scale Developer portal customizations/enhancements | Backlog
|  |  | 7.1.3 Check the themes, templates and other layout beautification standards at Erste Digital and its features availability on the desired tools | Backlog
|  |  | 7.1.4 Webserver and other runtime components standard practice identification at Erste Digital and Implementation Plan | Backlog
|  |  | 7.1.5 Web page hosting compliance check and its requirements while using identified design tools | Backlog
|  | 7.2 | Design the wireframe with all necessary features and its rough layout | Backlog | 15
|  |  | 7.2.1Capture the Internal Developer portal (Intranet) requirements with a draft UX design as D134 | Backlog
|  |  | Registration and Sign up for the portal to have identification as well to identify the user privileges and feedback | Backlog
|  |  | Discovery of API and Enterprise wide API search feature enablement | Backlog
|  |  | Registry of New and Existing APIs | Backlog
|  |  | Role based access privileges for API Development Team, Administration, Consumers, Providers and Others like internal partners (Erste Group) | Backlog
|  |  | Categorisation of APIs and the Contract (Open API Specifications - Swaggers) and populate them on API Sandbox (playground) | Backlog
|  |  | API Documentation - References, Onboarding Process, Consumer and Provider API Handbook about Usage, Configuration, Compliance such as PSD2, Open Banking etc | Backlog
|  |  | API Internal Community - Developers, Partners, SME's to provide feedback and exclusive requirements if any | Backlog
|  |  | API Monetization such as pricing and subscriptions, API Market place to promote API's re-usability, availability etc | Backlog
|  | 7.3 | Design the portal screen as prescribed in the UX/wireframes | Backlog | 30
|  |  | - UX Design Requirements gathering | Backlog
|  |  | Explain and handover all the requirements about the developer portal requirements to UX designer experts | Backlog
|  |  | Value proposition mapping about the requirements that is used by different user’s and the usage frequency | Backlog
|  |  | Concept sketching (optional since we already have the UX draft design) which covers the high-level outline of the product purpose | Backlog
|  |  | Creating actual wireframes by referring to the draft UX design to build workable/simulation prototype for all the portal screens/features | Backlog
|  |  | Creating Design Specifications for all of the visual design assets required for developers to turn prototypes into a working product | Backlog
|  |  | Creating design systems (Optional) which is for designers who typically create a system of components, patterns, and styles that help both designers and developers stay on the same page regarding the design which is as per Erste Digital Web Components Design Standards | Backlog
|  |  | Validation and Testing the complete prototype built with an accurate wireframes created as per the given standards and portal requirements | Backlog
|  | 7.4 | Simulate the data on to the designed developer portal | Backlog | 15
|  |  | Prototype alignment with the Digital Screens – HTML, CSS or desired technology for the responsive screen development | Backlog
|  |  | Selection of the standard aligned technology like HTML, JSP, Angular, CSS etc | Backlog
|  |  | Create a visual style for the overall visual style which will most likely be determined by the visual brand of the organization – Erste Digital | Backlog
|  |  | Site Development With designs approved, it’s time to flesh out the design of the pages, develop new content and refine old content, create videos, slideshows, podcasts and other media that will appear on the site as well as start to build out the HTML and CSS of the site | Backlog
|  |  | Developer portal Site Testing - Before the site is launched, it will be placed on a production server where only internal audiences and anyone who you share the link with can view it | Backlog
|  | 7.5 | Then see the options to build the back end for the developer portal data rendering, meta data storage etc | Backlog | 40
|  |  | Discover and define the technology used for the back end for Newly Developed Portal | Backlog
|  |  | Identify the different back end requirements like meta data storage, data rendering, cache management, API and service identification | Backlog
|  |  | Adoption of the back end technology such as micro-services for data rendering, pagination for feedbacks and other similar features, NodeJS, View Js and Spring Services, OSB, ECP calls etc | Backlog
|  |  | SSO, Identity and Access management solutions for the User Access and Role Based Access | Backlog
|  |  | Front End Package deployments on Web Server’s and Back End Services Deployments as part of Developer Portal end to end Testing with User Acceptance, Performance etc | Backlog
|  | 7.2 | Single Web APP (portal) possibility | Backlog | 0 |  |  |  | If RedHat cannot offer us the protal based on our requirements, MB+ alfa integrations
|  |  | 7.2.1 Integration with Alfa IDP | Backlog
|  |  | 7.2.2 Implementation of the webbportal | Backlog
|  |  | 7.2.3 Implementation of the clients API | Backlog
|  | 7.7 | API Feedback | Backlog | 15
|  |  | 7.7.1 Create rating tab | Backlog
|  |  | 7.7.2 Add Feedback/comment section | Backlog
|  |  | 7.7.3 NFRs and KPIs requirement gathering tab | Backlog
|  |  | 7.7.4 Consumer requirements to the provider or the API management team | Backlog
|  | 7.8 | API Marketplace | Backlog | 15
|  |  | 7.8.1 Define requriement and the Design | Backlog
|  |  | 7.8.2 implement the hub | Backlog
|  | 7.9 | API Following | Backlog | 5
|  |  | 7.9.1 Define how a cosnumer can follow an API | Backlog
|  |  | 7.9.2 Implement the channels to publish new features versions of an API | Backlog
8 ECP |  | 8.1 | Identify services | Backlog | 15 | Sourav
|  |  | Identify ECP services to be exposed as an API | Backlog |  | Sourav
|  |  | Identify OSB services to be exposed as an API | Backlog |  | Sourav
|  | 8.2 | Create APIs | Backlog |  | Ankita
|  |  | Create APIs for the identified ECP services and perform unit testing | Backlog | 30 | Ankita |  |  | Based on the no of APIs, it can be estimated. For now kept it 30
|  |  | Create APIs for the identified OSB services and perform unit testing | Backlog | 30 | Ankita |  |  | Based on the no of APIs, it can be estimated. For now kept it 30
|  | 8.3 | Testing of APIs | Backlog |  | Ahini
|  |  | Perform functional/load testing for all 3 scale APIs build for ECP and OSB | Backlog | 30 | Ahini |  |  | Based on the no of APIs, it can be estimated. For now kept it 30
|  |  |  | Total | 629